## Pre Bid Queries
Tender for Turnkey Supply Package for 5 nos. of 160 MVA, 220/33-33 kV Power Transformer at Radha Nesda, Gujarat, India
Tender No.: SECI/C&P/OP/11/04/2026-27
Sl. No. | Tender Section | Page No. | Clause No | Description as per Tender Document | Queries | Category (Technical/Contractual) | Clarifications
1 | SPECIAL PURCHASE CONDITIONS (SPC) | Page 9 of 10 | 16. Price Variation Clause | a. Offered Price shall be based on latest IEEMA -published Price Variation (PV) formula for Power Transformers of voltage above 33 kV and up to 400 kV supplied against domestic contracts (as on the last date of Bid Submission). b. This formula would attract an upper Price variation ceiling of 20% (Twenty Percent), beyond which no price variation would be provided. c. Further, no price variation would be provided to the Transformer supplier till any price variation upto 5% (Five Percent) price change. | As per the IEEMA Price Variation Indices, the variation during the last one year itself (April 2025 to May 2026) has been approximately 19.5%. The material cost components of transformers are highly volatile, and the proposed ceiling on price variation may not provide adequate coverage against fluctuations in the prices of major raw materials. Consequently, bidders would be required to factor this additional risk into their bid prices, resulting in a higher overall bid price. In view of the above, we request the Employer to consider allowing price adjustment without any ceiling on either upward or downward variation. This will facilitate more competitive and realistic pricing from bidders. Kindly confirm. | Contractual | The terms and conditions of the tender document shall prevail.
2 | BID INFORMATION SHEET | 13 | (H) EARNEST MONEY DEPOSIT (EMD) | INR 1,50,00,000/- Crores (Indian Rupees One Crores and Fifty Lakhs only) | We would like to submit that BHEL, being a Government of India enterprise and a Central Public Sector Undertaking (CPSU), has a well-established track record in the power sector, with consistent and reliable execution of projects for various utilities. Considering BHEL’s proven credentials, financial strength, and commitment to timely project execution, the requirement of submission of EMD in the form of a Bank Guarantee may kindly be waived. The primary objective of EMD is to ensure participation of serious and credible bidders; however, in the case of a CPSU of BHEL’s standing, this requirement does not serve any additional purpose. It is also pertinent to mention that several Central and State Utilities have already extended exemption from submission of EMD to CPSUs, recognizing that such requirements are not necessary for Government entities with established credibility and accountability. In view of the above, we request kind consideration to grant exemption from submission of EMD Bank Guarantee for the subject tender. This will help in avoiding additional financial burden and administrative costs, thereby ensuring more efficient utilization of financial resources. | Contractual | The terms and conditions of the tender document shall prevail.
3 | SPECIAL PURCHASE CONDITIONS (SPC) | Page 2 of 10 | Supplies at site | The total timeline for Completion for the entire 5 * 160 MVA, 220/33- 33 kV PT Package in total shall be 17 (seventeen) Months from the Date of the Purchase Order/Contract Agreement or Notice to Proceed (NTP), whichever is late | Considering the current market scenario and the scarcity of major raw materials required for transformer manufacturing, we request the Employer to extend the delivery schedule for transformers from the stipulated 17 months to at least 24–26 months. The extended delivery period will enable manufacturers to effectively manage procurement challenges, optimize production planning, and ensure timely execution of the contract without compromising quality and reliability. | Contractual | The terms and conditions of the tender document shall prevail.
4 | QUALIFYING REQUIREMENTS (QR) | Page 5 of 11 | 1.3 FINANCIAL ELIGIBILITY CONDITIONS | The Minimum Average Annual Turnover (MAAT) of the bidder in the last three financial years (i.e. FY 2022-23, 2023-24 & 2024-25)….AND The bidder should have a minimum Working Capital of INR 13.53 Crores (Indian Rupees Thirteen Crores and Fifty-Three Lakhs only) as per the last audited financial statement | For MAAT, last three finanicial years (i.e. FY 2022-23, 2023-24 & 2024-25) is mentioned ....while for minimum Working Capital it is the last audited financial statement. Please clarify whether for MAAT also the FY 2022-23, 2023-24 & 2024-25 is to be considered OR FY 2023-24, 2024-25 & 2025-26). | Contractual | Audited financial results i.e. Annual Report including Audited Balance Sheet and Profit & Loss Account Statement for immediate three preceding financial years to meet the above Financial Eligibility Criteria. In case of tenders having the submission deadline up to 30th September of the relevant financial year and audited financial results of immediate 3 preceding financial years being not available, the bidder has an option to submit the audited financial results of three years immediately prior to relevant financial year. In case the bid submission deadline is after 30th September of the relevant financial year, bidder has to compulsorily submit the audited financial results of immediately preceding three financial years.
5 | Pertaining to IEEMA PVC |  |  | No price variation would be provided to the Transformer supplier till any price variation up to 5% (Five Percent) price change. | We request SECI to agree variable price as per IEEMA without any ceiling. | Contractual | The terms and conditions of the tender document shall prevail.
6 | Pertaining to IEEMA PVC |  |  | Base date for the purpose of price variation to be considered: Last date of Bid Submission deadline. | As per IEEMA PV formula, base date is 1 month prior to the date of tendering. Please issue amendment for the same. | Contractual | The terms and conditions of the tender document shall prevail.
7 | Completion/ Contract Period |  |  | 17 Months | Due to long delivery period of bushings, we request SECI to revise delivery period to 24 months. | Contractual | The terms and conditions of the tender document shall prevail.
8 | General |  |  |  | We have considered CT details as per CEA Solar park pooling station, Annexure B (4.0) along with WTI CTs (1no for HV, 1no for LV1 & 1no for LV2). Kindly provide details for any specific requirement | Technical | Accepted. Terms and Condition of tender shall prevail.
9 | Cl. No. 21.0 of CEA Spec. |  |  |  | In absence of detail specification, We have not Considered Optical Temperature Sensors & Measuring Unit. | Technical | Accepted. Terms and Condition of tender shall prevail.
10 | Cl. 7.0 of CEA spec & Cl. 1.7.2 Section VII, Subsection –B, TS |  |  |  | Offered transformer meets short circuit similarity as per CEA, Annexure J with our 165 MVA, 220/33 KV transformer. It is currently at manufacturing stage and not yet undergone with short circuit test. Also, this transformer, on which short circuit test shall be carried out is with single LV while offered transformer is with Dual LV. Are we requiring to conduct SCT on transformer which will be supplied to SECI. | Technical | SCT shall be carried out on offered Transformer or a similar 220/33-33 Dual LV Transformer, as per CEA Specifications for Solar park pooling station, Annexure J.
11 | Cl. 12.0 of CEA Specification |  |  |  | Since detailed specification of Oil storage tank is not provided, we have not considered it in our offer | Technical | Accepted. Terms and Condition of tender shall prevail.

## Amendment
Tender for Turnkey Supply Package for 5 nos. of 160 MVA, 220/33-33 kV Power Transformer at Radha Nesda, Gujarat, India
Tender No.: SECI/C&P/OP/11/04/2026-27
Sl. No. | Tender Section | Page No. | Clause No | Description as per Tender Document | Amended Clause | Category (Technical/Contractual)
1 | SECTION - VII SUB-SECTION B TECHNICAL SPECIFICATIONS (TS) PURCHASE CONDITIONS (SPC) |  | 1.2 Technical Requirements | Parameters Inverter Transformer Vector Group and Neutral Earthing YNynyn0; All Neutral solidly Earthed | Parameters Power Transformer Vector Group and Neutral Earthing YNyn0yn0; All Neutral solidly Earthed | Technical